## Status Report
Project Name | PropOwner |  | Date |  | 2018-09-28 | Project Manager |  | Austin Hwang
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
To produce a usable Housing Management application for vendors, owners, and tennants. Focus will be placed on primarily the vendor application side, in which several views such as the vendor onboarding screen, vendor profile page, job request history view, and owner vendor search screen will be generated and connected to a central database. Firebase will be the database management storage, and flutter the framework that will contain dart code for multi-platform application creation. |  |  |  | Design vendor primary (home) view |  | 100% | Complete |  | 2018-10-01
|  |  |  | Download Frameworks (Flutter, Firebase) |  | 100% | Complete |  | 2018-10-02
|  |  |  | Organization of Flutter Files |  | 75% | On Track |  | 2018-10-12
|  |  |  | Implement basic Firebase mainframe |  | 50% | On Track |  | 2018-10-15
|  |  |  | Implement Vendor Profile Creation Page |  | 10% | Possible Delays |  | 2018-10-15
|  |  |  | Design Other Views |  | 0% | Future Task |  | 2018-10-22
|  |  |  | Implement Other Views |  | 0% | Future Task |  | 2018-11-19
[6 empty] | 0% | Delayed
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Generate more detailed architecture (through requirements doc), get more familiar with appropriate software (Flutter, Firebase), download software team computers, review front end main view sketch |  |  | Implement Vendor Profile Creation Page |  |  | Review and implement other UI main view design sketches, Gain more experience in Dart and Flutter, Start implementing Vendor Profile Creation Page
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Austin Hwang | Project Manager/Frontend Dev | 3.5 | Risk | Delay in creating initial view (Vendor Profile Creation Page)
Brandon Derbidge | Chief Architect/Middleware | 5
Autumn Chapman | QA/Test Manager | 3.7
David Corey | Middleware/Database | 1 | Issue | Unfamiliarity with software (Flutter/Dart) may cause initial delays in implementation as team members develop a learning curve. Progress in implementation expected to speed up over time.
Ali Harrison | UI Design/Frontend Dev | 5
Illiana Heaton | UI Design/Frontend Dev | 3
Total |  | 21.2

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task