## Status Report
Project Name | Housing Management |  | Date |  | 2018-09-21 | Project Manager |  | Austin Hwang
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
To produce a usable Housing Management application for vendors, owners, and tennants. Focus will be placed on primarily the vendor application side, in which several views such as the vendor profile creation page, request history, profile view, and owner vendor search views will be generated and connected to a central database. Firebase will be the database management storage, and flutter the framework that will contain dart code for multi-platform application creation. |  |  |  | Assign team roles and generate architecture |  | 100% | Complete |  | 2018-09-26
|  |  |  | Design vendor primary (home) view |  | 80% | On Track |  | 2018-10-01
|  |  |  | Download Frameworks (Flutter, Firebase) |  | 85% | On Track |  | 2018-10-02
|  |  |  | Implement basic Firebase mainframe |  | 40% | On Track |  | 2018-10-15
|  |  |  | Implement Vendor Profile Creation Page |  | 0% | Future Task |  | 2018-10-15
|  |  |  | Implement Other Views |  | 0% | Future Task |  | 2018-10-29
[6 empty] | 0% | Possible Delays
[6 empty] | 0% | Delayed
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Assign team roles, generate basic architecture, get familiar with appropriate software (Flutter, Firebase), download software on majority of team's computers, front end main view sketch |  |  | N/A |  |  | Finish downloading appropriate software, review and implement UI main view design sketches, gain more experience in Dart and Flutter
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Austin Hwang | Project Manager/Frontend Dev | 6 | Risk | N/A
Brandon Derbidge | Chief Architect/Middleware | 6
Autumn Chapman | QA/Test Manager | 2.5
David Corey | Middleware/Database | 5 | Issue | N/A
Ali Harrison | UI Design/Frontend Dev | 5
Illiana Heaton | UI Design/Frontend Dev | 5
Total |  | 29.5

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task