## Status Report
Project Name | PropOwner |  | Date |  | 2018-10-19 | Project Manager |  | Austin Hwang
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
To produce a usable Housing Management application for vendors, owners, and tennants. Focus will be placed on primarily the vendor application side, in which several views such as the vendor onboarding screen, vendor profile page, job request history view, and owner vendor search screen will be generated and connected to a central database. Firebase will be the database management storage, and flutter the framework that will contain dart code for multi-platform application creation. |  |  |  | Implement Vendor Profile Creation Page |  | 100% | Complete |  | 2018-10-19 | Complete
|  |  |  | Implement Vendor Profile Page |  | 100% | Complete |  | 2018-10-19 | On Track
|  |  |  | Design Wireframes for all Views |  | 100% | Complete |  | 2018-10-19 | Possible Delays
|  |  |  | Implement Owner Vendor Search View |  | 50% | On Track |  | 2018-10-29 | Delayed
|  |  |  | Implement Job History Page |  | 40% | On Track |  | 2018-10-29 | Future Task
|  |  |  | Redux State Layer |  | 0% | Possible Delays |  | 2018-10-25
|  |  |  | View Integration |  | 0% | Future Task |  | 2018-11-03
|  |  |  | Mock Data |  | 0% | Future Task |  | 2018-11-12
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Get more familiar with appropriate software (Flutter, Firebase), Implement the Vendor Profile Creation Page, Implement Vendor Profile Page, Design the wireframes for all Views |  |  | N/A |  |  | Complete the implementation of all views, integrate views together in preparation for the first demo (a skeleton version), create mock data in place of the firebase database so we have a workable demo
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Austin Hwang | Project Manager/Frontend Dev | 3 | Risk | After further research, we now have an understanding of how to integrate the Front end views with the Firebase database. Now we need to estimate how long that will take as we don't have a full understanding of its complexity.
Brandon Derbidge | Chief Architect/Middleware | 6
Autumn Chapman | QA/Test Manager | 1.5
David Corey | Middleware/Database | 5 | Issue | Determining if we will actually implement the redux state layer and create a layer between the front end UI and firebase. Signs pointing to no as it’s a feature we might have to take out due to time.
Ali Harrison | UI Design/Frontend Dev | 5
Illiana Heaton | UI Design/Frontend Dev | 5
Total |  | 25.5

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task