## Status Report
Project Name | PropOwner |  | Date |  | 2018-11-16 | Project Manager |  | Austin Hwang
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
To produce a usable Housing Management application for vendors, owners, and tennants. Focus will be placed on primarily the vendor application side, in which several views such as the vendor onboarding screen, vendor profile page, job request history view, and owner vendor search screen will be generated and connected to a central database. Firebase will be the database management storage, and flutter the framework that will contain dart code for multi-platform application creation. |  |  |  | View Integration |  | 100% | Complete |  | 2018-11-07 | Complete
|  |  |  | Implement Mock Data for Demo #1 |  | 100% | Complete |  | 2018-11-07 | On Track
|  |  |  | Demo #1 |  | 100% | Complete |  | 2018-11-10 | Possible Delays
|  |  |  | Connect to Firestore (Database) |  | 0% | Future Task |  | 2018-11-30 | Delayed
|  |  |  | Beta Testing |  | 0% | Future Task |  | 2018-12-07 | Future Task
|  |  |  | Finalize App for Demo #2 |  | 0% | Future Task |  | 2018-12-07
|  |  |  | Demo #2 |  | 0% | Future Task |  | 2018-12-10
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Finish view integration and functionality of switching view to view, Implement Mock Data for Demo #1, Practice demonstration for Demo #1 |  |  | N/A |  |  | Connect to Firestore (Database), Perform Beta Testing, Finalize App for Demo #2
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Austin Hwang | Project Manager/Frontend Dev | 1 | Risk | We might need to ramp up our hours after Demo #1 in case something doesn't go as planned during the integration phase (connecting the app to firestore).
Brandon Derbidge | Chief Architect/Middleware | 2
Autumn Chapman | QA/Test Manager | 0.6
David Corey | Middleware/Database | 1 | Issue | N/A
Ali Harrison | UI Design/Frontend Dev | 1.2
Illiana Heaton | UI Design/Frontend Dev | 1.5
Total |  | 7.3