## Status Report
Project Name | PropOwner |  | Date |  | 2018-10-26 | Project Manager |  | Austin Hwang
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
To produce a usable Housing Management application for vendors, owners, and tennants. Focus will be placed on primarily the vendor application side, in which several views such as the vendor onboarding screen, vendor profile page, job request history view, and owner vendor search screen will be generated and connected to a central database. Firebase will be the database management storage, and flutter the framework that will contain dart code for multi-platform application creation. |  |  |  | Implement Owner Vendor Search View |  | 100% | Complete |  | 2018-10-25 | Complete
|  |  |  | Implement Job History Page |  | 100% | Complete |  | 2018-10-25 | On Track
|  |  |  | Prepare Mock Data |  | 30% | On Track |  | 2018-10-31 | Possible Delays
|  |  |  | View Integration |  | 15% | On Track |  | 2018-11-03 | Delayed
|  |  |  | Implement Mock Data for Demo #1 |  | 0% | On Track |  | 2018-11-03 | Future Task
|  |  |  | Connect to Firestore (Database) |  | 0% | Future Task |  | 2018-11-16
|  |  |  | Beta Testing |  | 0% | Future Task |  | 2018-11-30
|  |  |  | Finalize App for Demo #2 |  | 0% | Future Task |  | 2018-12-07
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Implemented all front end UI pages, Implemented some functionality of switching view to view (began view integration), Finalized database storage |  |  | N/A |  |  | Prepare the type of mock data needed for Demo #1, Integrate views together in preparation for the first demo (a skeleton version), Implement the mock data into the skeleton demo, prepare for Demo #1 presentation
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Austin Hwang | Project Manager/Frontend Dev | 2.5 | Risk | As we begin the integration stage of the mock data to the wireframe we have created, we must be mindful of ensuring effective QA testing to prevent noticeable bugs in our first demo.
Brandon Derbidge | Chief Architect/Middleware | 7
Autumn Chapman | QA/Test Manager | 2.5
David Corey | Middleware/Database | 6 | Issue | N/A
Ali Harrison | UI Design/Frontend Dev | 3.1
Illiana Heaton | UI Design/Frontend Dev | 14
Total |  | 35.1

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task