## Status Report
Project Name | PropOwner |  | Date |  | 2018-10-05 | Project Manager |  | Austin Hwang
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
To produce a usable Housing Management application for vendors, owners, and tennants. Focus will be placed on primarily the vendor application side, in which several views such as the vendor onboarding screen, vendor profile page, job request history view, and owner vendor search screen will be generated and connected to a central database. Firebase will be the database management storage, and flutter the framework that will contain dart code for multi-platform application creation. |  |  |  | Organization of Flutter Files |  | 100% | Complete |  | 2018-10-09 | Complete
|  |  |  | Implement basic Firebase mainframe |  | 100% | Complete |  | 2018-10-09 | On Track
|  |  |  | Design Wireframes for all Views |  | 80% | On Track |  | 2018-10-17 | Possible Delays
|  |  |  | Implement Vendor Profile Creation Page |  | 70% | On Track |  | 2018-10-29 | Delayed
|  |  |  | Implement Vendor Profile Page |  | 10% | On Track |  | 2018-10-29 | Future Task
|  |  |  | Implement Job History Page |  | 30% | On Track |  | 2018-10-29
|  |  |  | Implement Database Design |  | 70% | On Track |  | 2018-10-18
|  |  |  | Redux State Layer |  | 0% | Future Task |  | 2018-10-25
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Generate more detailed projected timeline (through the Gantt and Pert charts), get more familiar with appropriate software (Flutter, Firebase), Organize existing Flutter files into a manageable manner, Implement the basic Firebase mainframe, Design wireframes for 3 of the 4 views |  |  | Owner Vendor Search Screen (waiting for other views to finish before implementation) |  |  | Complete wireframes/design to implement later on front end, Finish designing database to begun the implemenation of states (between front end and database), Start implementing Owner Vendor Search screen
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Austin Hwang | Project Manager/Frontend Dev | 7 | Risk | Integration of the Front end views with the Firebase database
Brandon Derbidge | Chief Architect/Middleware | 7
Autumn Chapman | QA/Test Manager | 6
David Corey | Middleware/Database | 7.2 | Issue | Unknown how much time the integration will take from the views->states->database until we gain familiarity and approach that problem
Ali Harrison | UI Design/Frontend Dev | 4.7
Illiana Heaton | UI Design/Frontend Dev | 6
Total |  | 37.9

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task